## Summary
VirtualOffice AI — Tracker Summary
Status | Count | Description
✅ Done | 100 | Shipped and deployed to staging
▶ Active | 0 | Currently in progress
○ Pending | 7 | Defined, not yet started
⏸ Deferred | 31 | Phase 4 — after Phase 3 ships
TOTAL | 138 | All tracked tasks
Completion | 72%
Immediate Blockers
GitHub repo creation | Pending | Needed for CI auto-deploy; add AWS_ACCESS_KEY_ID + AWS_SECRET_ACCESS_KEY as repo secrets
Terraform remote state | Deferred | S3 bucket already provisioned; run 'terraform init -migrate-state' when ready

## All Tasks
VirtualOffice AI — Product Tracker (generated 2026-07-05)
Phase | Sprint | Feature / Service | Sub-feature / Task | Status | Owner | Notes
Phase 1 — Foundation & Staging
P1 | S1 — Core Architecture | TypeScript Monorepo | pnpm workspaces + Turborepo, 19 packages | ✅ Done | Engineering
P1 | S1 — Core Architecture | TypeScript Monorepo | tsconfig references + noUncheckedIndexedAccess | ✅ Done | Engineering
P1 | S1 — Core Architecture | TypeScript Monorepo | ESLint + Prettier + Husky pre-commit | ✅ Done | Engineering
P1 | S1 — Core Architecture | Multi-tenant Data Layer | TenantContext explicit value type (ADR 007) | ✅ Done | Engineering | No AsyncLocalStorage
P1 | S1 — Core Architecture | Multi-tenant Data Layer | withTenant pattern — RLS via app.tenant_id | ✅ Done | Engineering
P1 | S1 — Core Architecture | Multi-tenant Data Layer | Two-role Postgres: voai_admin (migrations) + voai_app (runtime) | ✅ Done | Engineering
P1 | S1 — Core Architecture | Multi-tenant Data Layer | Row-Level Security FORCE on all tenant tables | ✅ Done | Engineering
P1 | S1 — Core Architecture | Multi-tenant Data Layer | pgvector extension for brain embeddings | ✅ Done | Engineering
P1 | S1 — Core Architecture | Local Dev Stack | Docker Compose: Postgres + pgvector + Redis + Neo4j | ✅ Done | Engineering
P1 | S1 — Core Architecture | Local Dev Stack | DB migration runner (node-pg-migrate) | ✅ Done | Engineering
P1 | S1 — Core Architecture | Local Dev Stack | Turborepo dev task with watch mode | ✅ Done | Engineering
P1 | S2 — Core Services | identity-and-tenancy | Tenant creation + scoped DB bootstrap | ✅ Done | Engineering
P1 | S2 — Core Services | identity-and-tenancy | User creation under tenant | ✅ Done | Engineering
P1 | S2 — Core Services | identity-and-tenancy | Session creation + TenantContext assembly | ✅ Done | Engineering
P1 | S2 — Core Services | brain | Memory storage (vector embeddings via pgvector) | ✅ Done | Engineering
P1 | S2 — Core Services | brain | Semantic search: retrieve relevant prior context | ✅ Done | Engineering
P1 | S2 — Core Services | brain | Neo4j graph: entity + relationship extraction | ✅ Done | Engineering
P1 | S2 — Core Services | brain | Brain context injected into agent prompts across sessions | ✅ Done | Engineering
P1 | S2 — Core Services | ledger | decisions table (type, summary, state) | ✅ Done | Engineering
P1 | S2 — Core Services | ledger | actions table (assigned_to, state, due_at) | ✅ Done | Engineering
P1 | S2 — Core Services | ledger | conflicts table (type, severity, resolution_state) | ✅ Done | Engineering
P1 | S2 — Core Services | ledger | CRUD endpoints for all three journal types | ✅ Done | Engineering
P1 | S2 — Core Services | routing | AnthropicProvider implementing LlmProvider interface | ✅ Done | Engineering
P1 | S2 — Core Services | routing | RoutingService: single seam for all LLM calls | ✅ Done | Engineering
P1 | S2 — Core Services | routing | Routing decision structured logging | ✅ Done | Engineering
P1 | S2 — Core Services | agent-runtime | Single-agent contribution (generateContribution) | ✅ Done | Engineering
P1 | S2 — Core Services | agent-runtime | Roster dispatch — fan-out to all personas in parallel | ✅ Done | Engineering
P1 | S2 — Core Services | agent-runtime | Persona: Rajan Mehta (CEO / Strategic Advisor) | ✅ Done | Product | Sarah Chen in code
P1 | S2 — Core Services | agent-runtime | Persona: Priya Reddy (CMO) | ✅ Done | Product
P1 | S2 — Core Services | agent-runtime | Persona: Marcus Webb (Devil's Advocate) | ✅ Done | Product
P1 | S2 — Core Services | agent-runtime | Brain context injection per-turn | ✅ Done | Engineering
P1 | S2 — Core Services | agent-runtime | Teammate awareness (no hallucinated names) | ✅ Done | Engineering
P1 | S2 — Core Services | meeting | Session create / get / list endpoints | ✅ Done | Engineering
P1 | S2 — Core Services | Demo Web UI | Thin React UI: send message, see 3 persona responses | ✅ Done | Product
P1 | S3 — Wave 3 Services | performance | 6-signal schema: factual_grounding, peer_agreement, expert_agreement, founder_action, outcome, pushback | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | performance | POST /signal — record a signal for a persona | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | performance | GET /scores/:personaId — aggregate by window (default 30d) | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | performance | GET /weekly — ranked weekly leaderboard | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | notification | notification_preferences table + RLS | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | notification | GET /briefing — Claude Haiku morning briefing (24h activity summary) | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | notification | GET/PUT /preferences — per-tenant briefing settings | ✅ Done | Engineering
P1 | S3 — Wave 3 Services | notification | POST /alert — log high-risk or conflict alert | ✅ Done | Engineering
P1 | S4 — AWS Staging | Infrastructure | ECR repository + IAM policy (AmazonEC2ContainerRegistryPowerUser) | ✅ Done | Infra
P1 | S4 — AWS Staging | Infrastructure | ECS Fargate cluster + task definition (linux/amd64) | ✅ Done | Infra | ADR 012: ECS over App Runner
P1 | S4 — AWS Staging | Infrastructure | Application Load Balancer + target group + /healthz health check | ✅ Done | Infra
P1 | S4 — AWS Staging | Infrastructure | RDS Postgres 16.9 (ap-south-1) | ✅ Done | Infra | 16.4 not available in region
P1 | S4 — AWS Staging | Infrastructure | ElastiCache Redis | ✅ Done | Infra
P1 | S4 — AWS Staging | Infrastructure | S3 object store bucket (voai-staging-objects) | ✅ Done | Infra
P1 | S4 — AWS Staging | Infrastructure | Secrets Manager: DATABASE_URL, MIGRATIONS_DATABASE_URL, REDIS_URL, NEO4J, ANTHROPIC_API_KEY | ✅ Done | Infra
P1 | S4 — AWS Staging | Infrastructure | VPC private subnets, security groups | ✅ Done | Infra
P1 | S4 — AWS Staging | Database | voai_admin + voai_app roles created on RDS | ✅ Done | Engineering
P1 | S4 — AWS Staging | Database | All 7 migrations applied (0000–0007) | ✅ Done | Engineering | Includes performance + notification
P1 | S4 — AWS Staging | Database | RLS policies active on staging RDS | ✅ Done | Engineering
P1 | S4 — AWS Staging | CI/CD | GitHub Actions deploy-staging.yml | ✅ Done | Engineering | Manual push currently; no GitHub remote yet
P1 | S4 — AWS Staging | CI/CD | GitHub remote + repo secrets (AWS keys) | ○ Pending | Engineering | Blocking full CI auto-deploy
Phase 2 — Live Meeting Intelligence
P2 | S5 — Response Gating | agent-runtime | checkShouldRespond() — Haiku gate, max 80 tokens, returns JSON {shouldRespond, relevanceScore, reason} | ✅ Done | Engineering | Deployed sprint5 tag
P2 | S5 — Response Gating | agent-runtime | generateRosterContributions — skip personas below 0.4 threshold | ✅ Done | Engineering
P2 | S5 — Response Gating | agent-runtime | Fail-open: JSON parse error → shouldRespond=true | ✅ Done | Engineering
P2 | S5 — Response Gating | agent-runtime | skipGate option for callers that need all-or-nothing dispatch | ✅ Done | Engineering
P2 | S5 — Response Gating | agent-runtime | Response includes skipped + gateResult per entry | ✅ Done | Engineering
P2 | S5 — Response Gating | Tests | Gate unit tests: skip on low score, fail-open on bad JSON, gateResult exposed | ✅ Done | Engineering | 22 tests total
P2 | S6 — Proactive Observer Loop | agent-runtime | observeSkippedPersonas(): re-score skipped personas with 0.65 threshold after roster completes | ✅ Done | Engineering | Deployed sprint6
P2 | S6 — Proactive Observer Loop | agent-runtime | Publish raise-hand event on EventBus (non-blocking, fire-and-forget) | ✅ Done | Engineering
P2 | S6 — Proactive Observer Loop | meeting | SseManager: track SSE connections per sessionId, fan-out on event | ✅ Done | Engineering
P2 | S6 — Proactive Observer Loop | meeting | SSE endpoint: GET /v1/meeting/sessions/:id/events (query-param auth for EventSource) | ✅ Done | Engineering
P2 | S6 — Proactive Observer Loop | meeting | Subscribe to raise-hand EventBus events → SseManager.emit() | ✅ Done | Engineering
P2 | S6 — Proactive Observer Loop | Demo UI | EventSource SSE connection on session start | ✅ Done | Product
P2 | S6 — Proactive Observer Loop | Demo UI | Yellow hand-raise bar with per-persona chips (name + confidence %) | ✅ Done | Product
P2 | S6 — Proactive Observer Loop | Demo UI | Click chip → fetch solo contribution; ✕ chip → dismiss | ✅ Done | Product
P2 | S7 — LLM Arbiter | agent-runtime | Arbiter: when ≥2 personas pass gate simultaneously, rank by (role relevance, silence penalty, perf score) | ✅ Done | Engineering | compositeScore = relevance×0.65 + silence×0.35
P2 | S7 — LLM Arbiter | agent-runtime | Ordered contribution queue — personas speak in ranked order, not parallel | ✅ Done | Engineering | generateOrderedContributions() with cumulative context
P2 | S7 — LLM Arbiter | agent-runtime | Configurable max-speakers-per-turn limit | ✅ Done | Engineering | DEFAULT_MAX_SPEAKERS=2
P2 | S7 — LLM Arbiter | performance | Silence penalty integration: use weekly score to boost quiet personas | ✅ Done | Engineering | silenceScore = min(minutesSilent/30, 1.0)
P2 | S8 — Voice Pipeline | Infrastructure | LiveKit Cloud account + project | ○ Pending | Infra | Requires manual account creation + LIVEKIT_* env vars
P2 | S8 — Voice Pipeline | Infrastructure | LiveKit room-per-session provisioning | ○ Pending | Infra | Token per session issued by meeting service
P2 | S8 — Voice Pipeline | Infrastructure | Deepgram streaming STT account + API key in Secrets Manager | ○ Pending | Infra | SDK wired; set DEEPGRAM_API_KEY to activate
P2 | S8 — Voice Pipeline | Infrastructure | ElevenLabs TTS account + voice IDs per persona | ○ Pending | Infra | SDK wired; set ELEVENLABS_API_KEY to activate
P2 | S8 — Voice Pipeline | media-coordinator | Audio pipeline coordinator: receive STT transcript chunks | ✅ Done | Engineering | apps/media-coordinator Express service on port 3001
P2 | S8 — Voice Pipeline | media-coordinator | Route transcript chunks to agent-runtime | ✅ Done | Engineering | pipeline.ts: STT → /v1/agent-runtime/contributions/roster
P2 | S8 — Voice Pipeline | media-coordinator | Receive agent text response → send to ElevenLabs TTS | ✅ Done | Engineering | tts.ts createTtsClient; graceful no-op when key absent
P2 | S8 — Voice Pipeline | media-coordinator | Play TTS audio back into LiveKit room track | ○ Pending | Engineering | Needs LiveKit Node SDK room join — deferred to native app
P2 | S8 — Voice Pipeline | meeting | LiveKit token generation endpoint (founder joins audio room) | ✅ Done | Engineering | POST /sessions/:id/voice-token → AccessToken JWT
P2 | S8 — Voice Pipeline | Demo UI | MediaRecorder audio → media-coordinator (no LiveKit browser SDK) | ✅ Done | Product | 250ms chunks; polls /status every 800ms
P2 | S8 — Voice Pipeline | Demo UI | Real-time transcript display (live chunk preview) | ✅ Done | Product | transcript-chunk div updated on each 800ms poll
P2 | S8 — Voice Pipeline | Demo UI | Persona voice labels (which voice is speaking) | ✅ Done | Product | voice-personas.ts maps name → ElevenLabs voice ID
Phase 3 — Expert Network & Marketplace
P3 | S9 — Expert Profiles & Matching | marketplace | Expert schema: domain tags, availability windows, rate card | ✅ Done | Engineering | migration 0008; expert_profiles + expert_domain_tags + expert_availability
P3 | S9 — Expert Profiles & Matching | marketplace | Expert onboarding flow (API) | ✅ Done | Product | POST /experts + PATCH /experts/:id + POST /experts/:id/tags
P3 | S9 — Expert Profiles & Matching | marketplace | Expert matching endpoint: given topic → ranked expert list | ✅ Done | Engineering | POST /match; token-overlap scoring; Phase 4 upgrades to vector similarity
P3 | S9 — Expert Profiles & Matching | marketplace | Escalation events: persona → real expert suggestion | ✅ Done | Engineering | POST /escalations + PATCH /escalations/:id (accept/dismiss)
P3 | S9 — Expert Profiles & Matching | agent-runtime | Persona can trigger 'escalate to real expert' action | ✅ Done | Engineering | POST /v1/agent-runtime/escalate; matchExperts + escalation.triggered event; sprint13
P3 | S9 — Expert Profiles & Matching | agent-runtime | Escalation event surfaced to founder in UI | ✅ Done | Product | Expert match chips in demo UI after each roster response; sprint14
P3 | S9 — Expert Profiles & Matching | brain | Expert domain knowledge indexed in Neo4j graph | ✅ Done | Engineering | graph.ts: (Expert)-[:HAS_DOMAIN]->(Domain); graphMatchExperts; 7 tests; sprint14
P3 | S10 — Expert Session Scheduling | scheduler | scheduler app: cron-style job runner | ✅ Done | Engineering | apps/scheduler; CronRunner; parseCron; shouldRun; 13 tests
P3 | S10 — Expert Session Scheduling | scheduler | Morning briefing cron job (08:00 UTC daily) | ✅ Done | Engineering | calls /internal/scheduler/morning-briefing on api-server
P3 | S10 — Expert Session Scheduling | marketplace | Expert availability slots API | ✅ Done | Engineering | GET /experts/:id/slots?date=YYYY-MM-DD → 30-min slot list
P3 | S10 — Expert Session Scheduling | marketplace | Expert session booking (Cal.com integration) | ✅ Done | Engineering | POST /experts/:id/book; Cal.com when CALCOM_API_KEY set
P3 | S10 — Expert Session Scheduling | meeting | Expert-join flow: invite expert to LiveKit room | ✅ Done | Engineering | POST /sessions/:id/expert-join-token; expert- identity; 2 tests; sprint15
P3 | S10 — Expert Session Scheduling | Demo UI | Expert availability picker + booking confirmation | ✅ Done | Product | Booking modal on escalation chip click; slot list + confirm; sprint15
P3 | S11 — Usage Metering & Billing | marketplace-metering | Token count per session stored in metering table | ✅ Done | Engineering | POST /events; llm_tokens + ai_roster_call event types
P3 | S11 — Usage Metering & Billing | marketplace-metering | Expert-minute billing events | ✅ Done | Engineering | POST /events with eventType=expert_minutes
P3 | S11 — Usage Metering & Billing | marketplace-metering | Monthly usage summary per tenant | ✅ Done | Engineering | GET /usage?from=&to= → UsageSummary; monthly_usage_rollup table
P3 | S11 — Usage Metering & Billing | Payments | Stripe subscription tiers (starter/growth/enterprise) | ✅ Done | Engineering | POST /billing/subscribe; stubs when STRIPE_SECRET_KEY absent
P3 | S11 — Usage Metering & Billing | Payments | Stripe charge per expert session | ✅ Done | Engineering | POST /billing/expert-charge; invoice items
P3 | S11 — Usage Metering & Billing | Payments | Expert payout (Stripe Connect) | ○ Pending | Engineering | Requires Stripe Connect onboarding — deferred to Phase 4
P3 | S11 — Usage Metering & Billing | routing | Token routing: track per-tenant LLM spend via RoutingService | ✅ Done | Engineering | RoutingService onUsage callback → recordMeteringEvent llm_tokens; sprint13
P3 | S12 — Admin Console | admin-console-api | Tenant provisioning endpoint — POST /tenants with x-admin-key auth | ✅ Done | Engineering | sprint12
P3 | S12 — Admin Console | admin-console-api | User management: invite, role assignment, deactivation | ⏸ Deferred | Engineering
P3 | S12 — Admin Console | admin-console-api | Usage dashboard — GET /tenants/:id/usage with metering breakdown | ✅ Done | Engineering | sprint12
P3 | S12 — Admin Console | admin-console-api | Seat-based subscription tier enforcement in routing layer | ⏸ Deferred | Engineering
P3 | S12 — Admin Console | Admin UI | Internal admin web app (separate from founder-facing demo UI) | ⏸ Deferred | Product
Phase 4 — Scale & Production Hardening (Deferred)
P4 | S13 — CI / DevOps | CI/CD | GitHub remote: create repo, push code, configure branch protection | ⏸ Deferred | Engineering | Manual deploy works; unblocking after Phase 2
P4 | S13 — CI / DevOps | CI/CD | GitHub Actions auto-deploy on push to main | ⏸ Deferred | Engineering | Workflow exists; needs AWS secrets in repo
P4 | S13 — CI / DevOps | CI/CD | Terraform remote state — S3 backend migration (1 command; bucket exists) | ⏸ Deferred | Infra
P4 | S13 — CI / DevOps | CI/CD | Staging smoke test job in CI pipeline | ⏸ Deferred | Engineering
P4 | S13 — CI / DevOps | IAM | Narrow IAM policy (scoped policy replacing broad managed policies) | ⏸ Deferred | Infra | Before co-founder / contractor access
P4 | S14 — Production Environment | Infra | prod VPC + separate RDS Multi-AZ instance | ⏸ Deferred | Infra
P4 | S14 — Production Environment | Infra | ECS desired-count 2 + ALB health-check tuning | ⏸ Deferred | Infra
P4 | S14 — Production Environment | Infra | Custom domain + ACM cert for ALB (HTTPS) | ⏸ Deferred | Infra
P4 | S14 — Production Environment | Infra | CloudFront CDN in front of ALB | ⏸ Deferred | Infra
P4 | S14 — Production Environment | Infra | WAF rules on ALB | ⏸ Deferred | Infra
P4 | S15 — Observability | Monitoring | CloudWatch dashboards: ECS CPU/mem, RDS connections, ALB latency | ⏸ Deferred | Infra
P4 | S15 — Observability | Monitoring | PagerDuty / SNS alerts on 5xx rate, task failures | ⏸ Deferred | Infra
P4 | S15 — Observability | Monitoring | Structured log search (CloudWatch Insights or Datadog) | ⏸ Deferred | Infra
P4 | S15 — Observability | Monitoring | Distributed trace IDs through routing + agent calls | ⏸ Deferred | Engineering
P4 | S16 — Multi-provider LLM Routing | routing | Four-tier LLM classification: Advanced / High / Good / OpenSource | ⏸ Deferred | Engineering | ADR — subscription-tier-driven routing
P4 | S16 — Multi-provider LLM Routing | routing | OpenAI provider implementation | ⏸ Deferred | Engineering
P4 | S16 — Multi-provider LLM Routing | routing | Bedrock provider implementation | ⏸ Deferred | Engineering
P4 | S16 — Multi-provider LLM Routing | routing | Failover: if primary provider errors, retry on next tier | ⏸ Deferred | Engineering
P4 | S16 — Multi-provider LLM Routing | routing | Cost-per-call tracking per provider per tenant | ⏸ Deferred | Engineering
P4 | S17 — Background Workers | worker | worker app: BullMQ job queue over Redis (apps/worker stub) | ⏸ Deferred | Engineering
P4 | S17 — Background Workers | worker | Async brain indexing (don't block meeting response) | ⏸ Deferred | Engineering
P4 | S17 — Background Workers | worker | Async Neo4j graph updates | ⏸ Deferred | Engineering
P4 | S17 — Background Workers | worker | Dead-letter queue + retry with exponential backoff | ⏸ Deferred | Engineering
P4 | S18 — Security & Compliance | Security | HTTPS enforcement (redirect HTTP → HTTPS at ALB) | ⏸ Deferred | Infra
P4 | S18 — Security & Compliance | Security | Secrets rotation (Secrets Manager auto-rotate) | ⏸ Deferred | Infra
P4 | S18 — Security & Compliance | Security | Pen test / OWASP audit before public launch | ⏸ Deferred | Engineering
P4 | S18 — Security & Compliance | Security | GDPR data deletion endpoint (tenant offboarding) | ⏸ Deferred | Engineering
P4 | S18 — Security & Compliance | Security | Audit log: every data write recorded with actor + timestamp | ⏸ Deferred | Engineering

## Credentials & Secrets
VirtualOffice AI — Credentials & Secrets Registry
Status | Service / Key | Env Var(s) | Stored In | How to Get It
✅ Have | Anthropic (Claude API) | ANTHROPIC_API_KEY | AWS Secrets Manager /voai/staging/anthropic-api-key | Already set in ECS task. Rotate at: console.anthropic.com → API Keys
✅ Have | AWS (ECS deploy + ECR) | AWS_ACCESS_KEY_ID AWS_SECRET_ACCESS_KEY | ~/.aws/credentials [voai-staging] | Already set locally. Add as GitHub repo secrets for CI: Settings → Secrets → Actions → New secret
✅ Have | PostgreSQL (RDS staging) | DATABASE_URL MIGRATIONS_DATABASE_URL | AWS Secrets Manager /voai/staging/database-url | Already provisioned on RDS ap-south-1. URL format: postgresql://voai_app:PASSWORD@HOST:5432/voai
✅ Have | Neo4j AuraDB | NEO4J_URI NEO4J_USER NEO4J_PASSWORD | AWS Secrets Manager /voai/staging/neo4j-* | Already provisioned at neo4j.io/cloud/aura-free. URI: neo4j+s://16c05d35.databases.neo4j.io
✅ Have | Redis (ElastiCache staging) | REDIS_URL | AWS Secrets Manager /voai/staging/redis-url | Already provisioned. URL format: redis://HOST:6379
✅ Have | LiveKit Cloud | LIVEKIT_URL LIVEKIT_API_KEY LIVEKIT_API_SECRET | AWS Secrets Manager /voai/staging/livekit-* (ECS task def :10) | ✅ Configured. Project: mysquad-3z2qrqie.livekit.cloud Rotate at: cloud.livekit.io → Settings → Keys
✅ Have | Deepgram (Speech-to-Text) | DEEPGRAM_API_KEY | AWS Secrets Manager /voai/staging/deepgram-api-key (ECS task def :11) | ✅ Configured. Rotate at: console.deepgram.com → API Keys
✅ Have | ElevenLabs — API Key | ELEVENLABS_API_KEY | AWS Secrets Manager /voai/staging/elevenlabs-api-key (ECS task def :12) | ✅ API key configured. Rotate at: elevenlabs.io → Profile → API Key
✅ Have | ElevenLabs — Voice IDs | VOICE_ID_SARAH VOICE_ID_PRIYA VOICE_ID_MARCUS | ECS task definition environment vars (task def :13) | ✅ Configured. Sarah: ecp3DWciuUyW7BYM7II1 Priya: ZqvIIuD5aI9JFejebHiH Marcus: bfGb7JTLUnZebZRiFYyq
🔴 Need | Stripe (Billing) | STRIPE_SECRET_KEY STRIPE_PRICE_STARTER STRIPE_PRICE_GROWTH STRIPE_PRICE_ENTERPRISE | AWS Secrets Manager (not yet created) | 1. Go to dashboard.stripe.com → Sign up / log in 2. Developers → API Keys → Copy Secret key (sk_live_... or sk_test_...) 3. Products → Add product → Create 3 products with recurring prices Copy each Price ID (price_xxx) for STARTER / GROWTH / ENTERPRISE 4. Store secret key in Secrets Manager 5. Add all 4 env vars to ECS task definition
🔴 Need | Cal.com (Expert scheduling) | CALCOM_API_KEY CALCOM_EVENT_TYPE_ID | ECS env var (not yet created) | 1. Go to cal.com → Sign up / log in 2. Settings → Developer → API Keys → Add new key 3. Event Types → Create event type (e.g. 'Expert Session 30min') Copy the numeric event type ID from the URL 4. Add both env vars to ECS task definition environment
✅ Have | GitHub repo | — (code pushed) | github.com/manuani/mysquad (main branch) | ✅ Repo created and code pushed. Remote: https://github.com/manuani/mysquad.git
🔴 Need | GitHub CI/CD secrets | AWS_ACCESS_KEY_ID AWS_SECRET_ACCESS_KEY | GitHub repo secrets (not yet added) | Run in terminal after gh auth login: gh secret set AWS_ACCESS_KEY_ID --repo manuani/mysquad --body "AWS_ACCESS_KEY_ID_REDACTED" gh secret set AWS_SECRET_ACCESS_KEY --repo manuani/mysquad --body "$(aws configure get aws_secret_access_key --profile voai-staging)" Then every push to main auto-deploys to ECS staging.
⚪ Optional | WorkOS (SSO / AuthKit) | WORKOS_API_KEY WORKOS_CLIENT_ID | AWS Secrets Manager (Phase 4) | 1. workos.com → Sign up → Dashboard → API Keys 2. Copy API Key + Client ID from your application 3. Configure redirect URIs to match your staging domain 4. Add both vars to ECS task definition (replaces dev-mode header auth)
⚪ Optional | AWS S3 (Object Store) | OBJECT_STORE_BUCKET OBJECT_STORE_ACCESS_KEY_ID OBJECT_STORE_SECRET_ACCESS_KEY OBJECT_STORE_REGION | ECS env (bucket already set) Secrets Manager for keys | Bucket already provisioned. Create a scoped IAM user for app access: IAM → Users → Create user → Attach S3 policy → Security credentials → Access key
⚪ Optional | Stripe Connect (Expert payouts) | STRIPE_CONNECT_CLIENT_ID | AWS Secrets Manager (Phase 4) | 1. dashboard.stripe.com → Connect → Get started 2. Platform profile → copy Client ID 3. Implement OAuth flow for experts to onboard their bank accounts
⚪ Optional | Admin API Key (internal) | ADMIN_API_KEY | ECS env var (default: dev-admin-key) | Generate a strong random key: openssl rand -hex 32 Set as ADMIN_API_KEY in ECS task definition environment. Share only with ops team — protects all /v1/admin/* endpoints
⚪ Optional | Scheduler Secret (internal) | SCHEDULER_SECRET | ECS env var (not yet set) | Generate: openssl rand -hex 32 Set same value in both scheduler service and api-server ECS envs. Used to authenticate x-scheduler-secret header on internal cron calls